## RFP overview
Request for Price / Bid Evaluation Overview
Project
Company Sole Point of Contact
Title / Position
Email
Subcontract name and number
Budget Cost
Currency
Contractor / Sub-Contractor | Approved supplier (Yes / No) | Contact | E-mail | Date ITT sent | Tender Return Date | Bid submittal date | Offer Validity - expiry date | Offer Value / Price
Contractor 1 |  |  |  | 2026-06-08 | 2026-06-29 | 2026-06-26 | 2026-07-26 | 0
Contractor 2 |  |  |  | 2026-06-08 | 2026-06-29 | 2026-06-24 | 2026-07-24 | 0
Contractor 3 |  |  |  | 2026-06-08 | 2026-06-29 | 2026-06-25 | 2026-07-25 | 0
Company / Tenderee / Purchaser's Actions
Ensure all Bidders are Approved or in the process of being Approved.
Ensure all Offers are still valid.
All RFP, offers and / or emails to be shared with Company sole point of contact listed above.
Formulas:
Tender Return Date = [Date ITT sent]+21
Bid submittal date = [Date ITT sent]+18
Offer Validity - expiry date = [Bid submittal date]+30

## Price Evaluation
Price Comparison - Bill of Quantities (BoQ)
Project | 0
Company Sole Point of Contact | 0
Title / Position | 0
Email | 0
Subcontract name and number | 0
Budget Cost | 0
Currency | 0
|  |  | Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Comments & Analysis
Activity | Quantity | Unit | Unit Rate | Total Price | Unit Rate | Total Price | Unit Rate | Total Price
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0
Sub-Total |  |  |  | 0 |  | 0 |  | 0
Grand Total (*) |  |  |  | 0 |  | 0 |  | 0
Budget cost
Contract cost (excluding internal assessed extra costs)
P&L Saving or Loss (+ / -) |  |  |  | 0 |  | 0 |  | 0
P&L Saving or Loss (% +/-) |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
Note on C34: The Company / Purhaser shall fill cell C9 in the sheet "RFP Overview" with the Cost Controller PRIOR to launching any RFP.

## Technical Evaluation
Technical Evaluation
Project | 0
Company Sole Point of Contact | 0
Title / Position | 0
Email | 0
Subcontract name and number | 0
Budget Cost | 0
Currency | 0
(*) The items below are provided as example, they need to be defined after review of the offers, with the Technical responsible/lead(s) & the Project Manager (PM).
Tenderer |  | Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Comments & Analysis
Technical Evaluation Criteria | Weighting | Rating | Points | Rating | Points | Rating | Points
a. Experience of similar projects | 15% | 1 | 0.15 | 1 | 0.15 | 1 | 0.15
b. Labour Resource & Plant Availability | 25% | 1 | 0.25 | 1 | 0.25 | 1 | 0.25
c. Programme | 30% | 1 | 0.3 | 1 | 0.3 | 1 | 0.3
d. QHSE | 15% | 1 | 0.15 | 1 | 0.15 | 1 | 0.15
e. Design Risk | 15% | 1 | 0.15 | 1 | 0.15 | 1 | 0.15
|  |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0
Sub-Total Technical (*) | 100% |  | 1 |  | 1 |  | 1 | This value is taken into consideration in the FINAL Evaluation sheet
|  | (*) | pls check the formula includes all lines above if you add any new lines
Rating: | 0 | Not Acceptable
| 1 | Acceptable, but need clarifications
| 2 | Acceptable
Criteria, weighting and rating shall be proposed by Technical responsible at RFP preparation meeting and agreed by Purchaser

## CommercialContractua Evaluation
Commercial & Contractual Evaluation
Project | 0
Company Sole Point of Contact | 0
Title / Position | 0
Email | 0
Subcontract name and number | 0
Budget Cost | 0
Currency | 0
(*) The items below are provided as example, they need to be defined after review of the offers, with the Technical responsible/lead(s) & the Project Manager (PM).
Tenderer |  | Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Comments & Analysis
Commercial/Contractual evaluation criteria | Weighting | Rating | Points | Rating | Points | Rating | Points
Availability of spread/equipment for the working period | 10% | 1 | 0.1 | 1 | 0.1 | 1 | 0.1
Received reference list of contracts and CV of key personnel | 10% | 1 | 0.1 | 1 | 0.1 | 1 | 0.1
Priority/ work load other projects | 10% | 1 | 0.1 | 1 | 0.1 | 1 | 0.1
Received procedures and method statement(s) | 10% | 1 | 0.1 | 1 | 0.1 | 1 | 0.1
Received schedule of activities |  | 1 | 0 | 1 | 0 | 1 | 0
Time needed from contract award to mobilisation | 10% | 1 | 0.1 | 1 | 0.1 | 1 | 0.1
Received a Project execution plan and a detailed time schedule |  | 1 | 0 | 1 | 0 | 1 | 0
Received firm (2) or budgetary (0) offer | 10% | 1 | 0.1 | 1 | 0.1 | 1 | 0.1
Received a description of its Quality Assurance System and Health Safety & Environment System |  | 1 | 0 | 1 | 0 | 1 | 0
Received a description of the Quality Records system proposed |  | 1 | 0 | 1 | 0 | 1 | 0
Validity of offer | 10% | 1 | 0.1 | 1 | 0.1 | 1 | 0.1
Payment Term duration | 10% | 1 | 0.1 | 1 | 0.1 | 1 | 0.1
Length of Warranty | 10% | 1 | 0.1 | 1 | 0.1 | 1 | 0.1
Commercial Risks due to historically many VO sent / lack of Bank guarantees / not good financial results | 10% | 1 | 0.1 | 1 | 0.1 | 1 | 0.1
Sub-Total Commercial (*) | 100% |  | 1 |  | 1 |  | 1 | This value is taken into consideration in the FINAL Evaluation sheet.
| check Weighting total should be 100% |  | (*) Check the formula includes all lines above if you add any new lines
Rating: | 0 | Not Acceptable
| 1 | Acceptable, but need clarifications
| 2 | Acceptable
Criteria, weighting and rating shall be proposed by Contract Manager, Quantity Surveyor, Lawyer (if applicable) and Project Manager & agreed by Purchaser

## Final Evaluation
Final Evaluation and Recommendation
Project | 0
Company Sole Point of Contact | 0
Title / Position | 0
Email | 0
Subcontract name and number | 0
Budget Cost | 0
Currency | 0
All CELLS in GREEN shall not be modified : AUTOMATIC FORMULAS
Weighting total should be 100%
| Contractor 1 | Contractor 2 | Contractor 3 | WEIGHTING, % | 100% | Min | Max
TECHNICAL EVALUATION |  |  |  | 25%
Technical score | 1 | 1 | 1 |  |  | 1 | 1
Normalised Result - points | 100 | 100 | 100 |  |  | 100 | 100
Final technical score | 25 | 25 | 25 |  |  | 25 | 25
Technical ranking | 1 | 1 | 1 |  |  | 1 | 1
COMMERCIAL EVALUATION |  |  |  | 25%
Commercial score | 1 | 1 | 1 |  |  | 1 | 1
Normalised Result - points | 100 | 100 | 100 |  |  | 100 | 100
Final commercial score | 25 | 25 | 25 |  |  | 25 | 25
Commercial ranking | 1 | 1 | 1 |  |  | 1 | 1
PRICE EVALUATION |  |  |  | 50%
Total Contract Value | 0 | 0 | 0 |  |  | 0 | 0
Normalised Result - points | 0 | 0 | 0 |  |  | 0 | 0
Final commercial score | 0 | 0 | 0 |  |  | 0 | 0
Commercial ranking | excl | excl | excl |  |  | 0 | 0
Total score | 50 | 50 | 50 | out of 100 |  | 50 | 50
Ranking, total | 1 | 1 | 1 |  |  | 1 | 1
Info: % difference compared to cheapest offer | excl | excl | excl
| Contractor 1 | Contractor 2 | Contractor 3
Final technical score | 25 | 25 | 25
Final commercial score | 25 | 25 | 25
Final price score | 0 | 0 | 0
Company / Tenderee / Purchaser remark (if any):
Based on this analysis, we should award to the supplier RANKED 1 in the line 34 since the assessments is complete and based on all possible criteria : techncial / commercial / financial /risk/....
Should award to the Supplier / Contractor ranked 1